## Sheet1
User story | Story points | Buiness value | ROI
As a registrant I want to register athletes manually Baseline story | 3
As a time keeper I want to start a timer for the given race so that timing is possible. | 2
As a time keeper I want to see the running timer for the given race so that I can follow the time and know that the timing works. | 1
As a time keeper I want to be able to save the time as a certain point is passed. | 3
As a time keeper I want the time automatically saved during a race so I don't have to do it manually
As an administrator I want to register name and distance of a race. | 3
As a registrant I want to connect participants to the proper races. | 5
As a registrant I want to assign a start number to each participant so that they can be uniquely identified in the event/competition. | 3
As a registrant I want to be able to print a list of participants in a club together with their start number, so that the clubs can give the start numbers to the participants. | 5
As a registrant I want to register participant start numbers in a list as they cross the finish line so that we know which order they finished in | 2
As an administrator I want to merge the time results and the order of the starting number at the finish, so I get a merged list with finishing time and the corresponding correct starting number
As a registrant I want to mark participants as present so that they can participate. | 2
As a time keeper I want to stop a started timer for the given race so that timing stops. | 2
As an administrator I want to register classes with unique names so that I can group participants. | 3
As a registrant I want to assign each participant to a single class so that they can run in races for the given class. | 2
As a time keeper I want to reset a timer for the given race so that timing can be restarted from the beginning. | 2
As an administrator I want to import a list of athletes and classes. | 13
As an administrator I want to import a list of races | 8
As an administrator I want to be notified if something is going wroing during import so that I know what data did'nt get imported
As an administrator I want to assign athletes to a race automatically when importing so I don’t have to do it manually | 8
As a registrant I want to update information about existing participants so that their information is correct. | 3
As a registrant I want to be able to look up the athletes so that I can check if a particular athlete is in the list of participants. | 5
As a speaker I want to see a list of present participants for a given race so that I can announce them. | 3
As a speaker I want to see the initial result and the official result of the race so that I can announce them. | 3
As an administrator I want to approve the initial result so that it becomes the official result. | 2
As an administrator I want to mark participants with a status (disqualified(DSQ), did not show up/ did not start(DNS), did not finish(DNF)) so that I can sort them in the results. | 3
As an administrator I should not be able to sort participants below a certain age by time in the results. | 2
As an administrator I want to be able to edit the resultlist so that any changes can be made
As a registrant I want to be able to register name and number of the person who receives the list of participants and numbers, so that we can reach them in case someone asks for the start numbers. | 3
Group:
As an administrator I want to check that the participant's club has paid their fee so that the participant is eligible for the regional championship. | 2
As an administrator I want to check that the participant is registered to his/her club so that the participant is eligible for the regional championship. | 2
As a registrant I want to be warned if registering an already registered athlete, so that I can choose to make the registration or not. | 3
As a speaker I want to see the running timer for the given race so that I can follow the time and know that the timing works. | 2
As an administrator I want to store the result of the race so that I can access it later. | 3
As a registrant I want to look up athletes from a list of previously registered athletes and add them to the participant list so that I don't have to type them manually.
As an administrator I want to import external lists of athletes so that any registrant can access them during manual registration of participants.
As a spectator I want to see the running timer for the given race, so that I can follow the time.
As a spectator I want to see the result in real time so that I can follow the event live.
User stories not estimated (but still very important requirement the system must fulfill)
As an administrator I want to be able to run the timing part of the system without Internet connection so that I can use it in the field.
As an administrator I want to run parts of the functionality of the system on a separate computer so that I don't have to share a computer with other persons.
As an administrator I want to set up the system locally so that it is not affected by other administrators running the system other places.